## CSF 2.0 Scorecard
NIST CYBERSECURITY FRAMEWORK 2.0 — SELF-ASSESSMENT SCORECARD
Company: HealthBridge Medical Supplies ¦ Prepared by: Nithin Joseph ¦ Assessment Date: June 2026 ¦ Framework: NIST CSF 2.0
Function | Category | Cat. ID | Sub. ID | Subcategory Description | Current Tier | Target Tier | Gap | Priority | Notes / Evidence
GV | Organizational Context | GV.OC | GV.OC-01 | Organizational mission is understood and informs cybersecurity risk management | Tier 3 – Repeatable | Tier 4 – Adaptive | 1 | Medium | Mission documented; not fully integrated into risk decisions
| Organizational Context | GV.OC | GV.OC-02 | Internal/external stakeholders with cybersecurity roles are identified | Tier 2 – Risk Informed | Tier 4 – Adaptive | 2 | High | Partial RACI exists; third-party roles not defined
| Organizational Context | GV.OC | GV.OC-03 | Legal, regulatory, and contractual cybersecurity obligations are understood | Tier 2 – Risk Informed | Tier 3 – Repeatable | 1 | Medium | HIPAA obligations noted; PCI-DSS review pending
| Risk Management Strategy | GV.RM | GV.RM-01 | Risk management objectives are established and agreed upon | Tier 2 – Risk Informed | Tier 4 – Adaptive | 2 | High | Informal objectives; no board-approved risk appetite
| Risk Management Strategy | GV.RM | GV.RM-02 | Risk appetite and tolerances are determined, communicated, and reviewed | Tier 1 – Partial | Tier 3 – Repeatable | 2 | High | No documented risk appetite statement
| Roles & Responsibilities | GV.RR | GV.RR-01 | Cybersecurity roles and responsibilities are established and communicated | Tier 2 – Risk Informed | Tier 3 – Repeatable | 1 | Medium | IT handles security ad hoc; no CISO or security lead assigned
| Roles & Responsibilities | GV.RR | GV.RR-02 | Cybersecurity roles are coordinated and aligned with third parties | Tier 1 – Partial | Tier 3 – Repeatable | 2 | High | No vendor security responsibility defined in contracts
| Policy | GV.PO | GV.PO-01 | Policy for managing cybersecurity risks is established, communicated, and enforced | Tier 2 – Risk Informed | Tier 3 – Repeatable | 1 | Medium | Informal policies exist; not formally approved or enforced
| Policy | GV.PO | GV.PO-02 | Policy is reviewed, updated, communicated, and enforced | Tier 1 – Partial | Tier 3 – Repeatable | 2 | High | No policy review cycle established
| Oversight | GV.OV | GV.OV-01 | Cybersecurity review outcomes are communicated to stakeholders | Tier 2 – Risk Informed | Tier 3 – Repeatable | 1 | Medium | Occasional reports to management; no formal cadence
ID | Asset Management | ID.AM | ID.AM-01 | Inventories of hardware managed by the organization are maintained | Tier 2 – Risk Informed | Tier 3 – Repeatable | 1 | Medium | Spreadsheet-based inventory; not automated or real-time
| Asset Management | ID.AM | ID.AM-02 | Inventories of software, services, and systems are maintained | Tier 2 – Risk Informed | Tier 3 – Repeatable | 1 | Medium | Partial software inventory; SaaS apps not tracked
| Asset Management | ID.AM | ID.AM-03 | Representations of the organization's network and data flows are maintained | Tier 1 – Partial | Tier 3 – Repeatable | 2 | High | No network diagram; data flows undocumented
| Asset Management | ID.AM | ID.AM-07 | Inventories of data and corresponding metadata for designated data types are maintained | Tier 1 – Partial | Tier 3 – Repeatable | 2 | High | No formal data classification or inventory
| Risk Assessment | ID.RA | ID.RA-01 | Vulnerabilities in assets are identified, validated, and recorded | Tier 2 – Risk Informed | Tier 3 – Repeatable | 1 | Medium | Ad hoc vulnerability scans; no formal process
| Risk Assessment | ID.RA | ID.RA-02 | Cyber threat intelligence is received from information sharing forums | Tier 1 – Partial | Tier 3 – Repeatable | 2 | High | No threat intel subscription or ISAC membership
| Risk Assessment | ID.RA | ID.RA-03 | Internal and external threats to the organization are identified and recorded | Tier 2 – Risk Informed | Tier 3 – Repeatable | 1 | Medium | Annual informal threat review only
| Risk Assessment | ID.RA | ID.RA-05 | Threats, vulnerabilities, likelihoods, and impacts are prioritized | Tier 2 – Risk Informed | Tier 3 – Repeatable | 1 | Medium | Risk register exists but not formally prioritized
| Improvement | ID.IM | ID.IM-01 | Improvements are identified from security assessments | Tier 2 – Risk Informed | Tier 3 – Repeatable | 1 | Medium | Post-incident reviews occur; no formal improvement tracking
PR | Identity Management | PR.AA | PR.AA-01 | Identities and credentials are issued, managed, verified, and revoked | Tier 2 – Risk Informed | Tier 3 – Repeatable | 1 | Medium | AD-managed identities; offboarding process inconsistent
| Identity Management | PR.AA | PR.AA-02 | Identities are proofed and bound to credentials based on context | Tier 2 – Risk Informed | Tier 3 – Repeatable | 1 | Medium | No MFA enforced on all systems; VPN lacks MFA
| Identity Management | PR.AA | PR.AA-05 | Access permissions and authorizations are managed, incorporating least-privilege | Tier 2 – Risk Informed | Tier 3 – Repeatable | 1 | Medium | Role-based access exists; not reviewed annually
| Awareness & Training | PR.AT | PR.AT-01 | Personnel are provided with awareness and training so they can perform cybersecurity tasks | Tier 2 – Risk Informed | Tier 3 – Repeatable | 1 | Medium | Annual training done; no phishing simulation
| Awareness & Training | PR.AT | PR.AT-02 | Individuals with responsibilities for high-risk roles receive additional training | Tier 1 – Partial | Tier 3 – Repeatable | 2 | High | No role-specific training for IT or finance staff
| Data Security | PR.DS | PR.DS-01 | Data-at-rest are protected | Tier 2 – Risk Informed | Tier 3 – Repeatable | 1 | Medium | Server-side encryption enabled; endpoint encryption partial
| Data Security | PR.DS | PR.DS-02 | Data-in-transit are protected | Tier 3 – Repeatable | Tier 4 – Adaptive | 1 | Medium | TLS enforced on web apps; internal traffic not always encrypted
| Data Security | PR.DS | PR.DS-10 | Data are destroyed according to policy | Tier 1 – Partial | Tier 3 – Repeatable | 2 | High | No data destruction or retention policy documented
| Platform Security | PR.PS | PR.PS-01 | Configuration management practices are established and applied | Tier 2 – Risk Informed | Tier 3 – Repeatable | 1 | Medium | Manual configs; no baseline or CIS benchmark applied
| Platform Security | PR.PS | PR.PS-02 | Software is maintained, replaced, and removed commensurate with risk | Tier 2 – Risk Informed | Tier 3 – Repeatable | 1 | Medium | Patches applied manually; no automated patch management
| Technology Infrastructure | PR.IR | PR.IR-01 | Networks and environments are protected from unauthorized logical access | Tier 2 – Risk Informed | Tier 3 – Repeatable | 1 | Medium | Firewall in place; no network segmentation
DE | Continuous Monitoring | DE.CM | DE.CM-01 | Networks and network services are monitored to find potentially adverse events | Tier 1 – Partial | Tier 3 – Repeatable | 2 | High | No SIEM or centralized log monitoring
| Continuous Monitoring | DE.CM | DE.CM-03 | Personnel activity and technology usage are monitored to find potentially adverse events | Tier 1 – Partial | Tier 3 – Repeatable | 2 | High | No DLP or user activity monitoring
| Continuous Monitoring | DE.CM | DE.CM-06 | External service provider activities are monitored to find potentially adverse events | Tier 1 – Partial | Tier 3 – Repeatable | 2 | High | No vendor monitoring or access logging
| Continuous Monitoring | DE.CM | DE.CM-09 | Computing hardware and software are monitored to find potentially adverse events | Tier 2 – Risk Informed | Tier 3 – Repeatable | 1 | Medium | AV deployed; no EDR or advanced endpoint monitoring
| Adverse Event Analysis | DE.AE | DE.AE-02 | Potentially adverse events are analyzed to characterize the events | Tier 1 – Partial | Tier 3 – Repeatable | 2 | High | No formal triage process; events handled ad hoc
| Adverse Event Analysis | DE.AE | DE.AE-03 | Information is correlated from multiple sources | Tier 1 – Partial | Tier 3 – Repeatable | 2 | High | No log correlation; siloed tools
| Adverse Event Analysis | DE.AE | DE.AE-06 | Information on adverse events is provided to authorized staff and tools | Tier 2 – Risk Informed | Tier 3 – Repeatable | 1 | Medium | Email alerts from AV only; no escalation workflow
RS | Incident Management | RS.MA | RS.MA-01 | The incident response plan is executed in coordination with relevant third parties | Tier 1 – Partial | Tier 3 – Repeatable | 2 | High | No documented IR plan; response is ad hoc
| Incident Management | RS.MA | RS.MA-02 | Incidents are triaged to support triage and escalation | Tier 1 – Partial | Tier 3 – Repeatable | 2 | High | No severity classification criteria defined
| Incident Management | RS.MA | RS.MA-04 | Incidents are escalated or elevated as needed | Tier 1 – Partial | Tier 3 – Repeatable | 2 | High | No escalation matrix or on-call process
| Incident Analysis | RS.AN | RS.AN-03 | Analysis is performed to establish what has occurred during an incident | Tier 2 – Risk Informed | Tier 3 – Repeatable | 1 | Medium | Post-incident analysis done informally; no standard template
| Incident Analysis | RS.AN | RS.AN-06 | Actions performed during an investigation are recorded | Tier 1 – Partial | Tier 3 – Repeatable | 2 | High | No chain of custody or evidence logging process
| Incident Response Reporting | RS.CO | RS.CO-02 | Internal and external stakeholders are notified of incidents as required | Tier 2 – Risk Informed | Tier 3 – Repeatable | 1 | Medium | Ad hoc notifications; no breach notification SOP
| Incident Mitigation | RS.MI | RS.MI-01 | Incidents are contained | Tier 2 – Risk Informed | Tier 3 – Repeatable | 1 | Medium | Manual containment steps; no playbooks
| Incident Mitigation | RS.MI | RS.MI-02 | Incidents are eradicated | Tier 2 – Risk Informed | Tier 3 – Repeatable | 1 | Medium | Eradication done case-by-case; undocumented
RC | Incident Recovery Plan | RC.RP | RC.RP-01 | The recovery portion of the incident response plan is executed once initiated | Tier 1 – Partial | Tier 3 – Repeatable | 2 | High | No BCP or DRP documented
| Incident Recovery Plan | RC.RP | RC.RP-03 | The integrity of backups and other restoration assets is verified before using them | Tier 1 – Partial | Tier 3 – Repeatable | 2 | High | Backups exist but never tested for restorability
| Incident Recovery Plan | RC.RP | RC.RP-04 | Critical mission functions and cybersecurity considerations are established during recovery | Tier 1 – Partial | Tier 3 – Repeatable | 2 | High | No RTO/RPO defined for any system
| Incident Recovery Plan | RC.RP | RC.RP-05 | The integrity and security of assets is verified after all recovery activities | Tier 1 – Partial | Tier 3 – Repeatable | 2 | High | No post-recovery verification checklist
| Incident Recovery Communication | RC.CO | RC.CO-03 | Recovery activities and progress in restoring operations are communicated to stakeholders | Tier 1 – Partial | Tier 3 – Repeatable | 2 | High | No stakeholder communication plan for recovery
| Improvements | RC.IM | RC.IM-01 | Recovery plans incorporate lessons learned | Tier 2 – Risk Informed | Tier 3 – Repeatable | 1 | Medium | Informal lessons learned; not fed back into plans

## Gap Analysis
GAP ANALYSIS BY CSF FUNCTION
Function | Full Name | # Subcats | Avg Current | Avg Target | High-Pri Gaps | Status | Top Action Item
GV | GOVERN | 10 | 1.8 | 3.3 | 5 | Needs Attention | Document and approve a formal risk appetite statement
ID | IDENTIFY | 9 | 1.7 | 3 | 3 | Needs Attention | Build an asset inventory and network diagram
PR | PROTECT | 11 | 1.9 | 3.1 | 2 | In Progress | Enforce MFA across all systems; implement patch management
DE | DETECT | 7 | 1.3 | 3 | 5 | Critical | Deploy SIEM for centralized log monitoring
RS | RESPOND | 8 | 1.5 | 3 | 4 | Critical | Create and test an incident response plan
RC | RECOVER | 6 | 1.2 | 3 | 5 | Critical | Document BCP/DRP with defined RTOs and RPOs
Tier | Label | Description
1 | Tier 1 – Partial | Ad hoc, reactive; risk management not formalized
2 | Tier 2 – Risk Informed | Risk practices approved but not organization-wide policy
3 | Tier 3 – Repeatable | Formal policies; consistently implemented across organization
4 | Tier 4 – Adaptive | Continuously improving; risk-aware culture; lessons integrated

## Remediation Roadmap
REMEDIATION ROADMAP — Prioritized Action Plan
Sorted by Priority (High → Low) then by Function. Review quarterly. Update Status as items are completed.
# | Function | Sub. ID | Subcategory | Current | Target | Gap | Recommended Action | Owner | Timeline
1 | GV | GV.OC-02 | Internal/external stakeholders with cybersecurity roles are identified | Tier 2 – Risk Informed | Tier 4 – Adaptive | 2 | Review and implement controls per NIST CSF guidance | IT Manager | Q4 2026
2 | GV | GV.RM-01 | Risk management objectives are established and agreed upon | Tier 2 – Risk Informed | Tier 4 – Adaptive | 2 | Review and implement controls per NIST CSF guidance | IT Manager | Q4 2026
3 | GV | GV.RM-02 | Risk appetite and tolerances are determined, communicated, and reviewed | Tier 1 – Partial | Tier 3 – Repeatable | 2 | Document risk appetite statement; present to board for approval | CISO / Leadership | Q3 2026
4 | GV | GV.RR-02 | Cybersecurity roles are coordinated and aligned with third parties | Tier 1 – Partial | Tier 3 – Repeatable | 2 | Update vendor contracts to include security responsibilities and SLAs | Legal / Procurement | Q3 2026
5 | GV | GV.PO-02 | Policy is reviewed, updated, communicated, and enforced | Tier 1 – Partial | Tier 3 – Repeatable | 2 | Establish annual policy review cycle; assign policy owners | Compliance Officer | Q3 2026
6 | ID | ID.AM-03 | Representations of the organization's network and data flows are maintained | Tier 1 – Partial | Tier 3 – Repeatable | 2 | Create network diagram and data flow map; review semi-annually | IT Manager | Q3 2026
7 | ID | ID.AM-07 | Inventories of data and corresponding metadata for designated data types are maintained | Tier 1 – Partial | Tier 3 – Repeatable | 2 | Implement data classification policy; tag all ePHI and PII | Compliance Officer | Q4 2026
8 | ID | ID.RA-02 | Cyber threat intelligence is received from information sharing forums | Tier 1 – Partial | Tier 3 – Repeatable | 2 | Join FS-ISAC or HH-ISAC for threat intelligence sharing | IT Security | Q4 2026
9 | PR | PR.AT-02 | Individuals with responsibilities for high-risk roles receive additional training | Tier 1 – Partial | Tier 3 – Repeatable | 2 | Develop role-specific training for IT staff, finance, and HR | HR / IT Security | Q4 2026
10 | PR | PR.DS-10 | Data are destroyed according to policy | Tier 1 – Partial | Tier 3 – Repeatable | 2 | Draft and implement data retention and destruction policy | Compliance Officer | Q4 2026
11 | DE | DE.CM-01 | Networks and network services are monitored to find potentially adverse events | Tier 1 – Partial | Tier 3 – Repeatable | 2 | Deploy SIEM (e.g. Splunk Free / Microsoft Sentinel) for log monitoring | IT Security | Q4 2026
12 | DE | DE.CM-03 | Personnel activity and technology usage are monitored to find potentially adverse events | Tier 1 – Partial | Tier 3 – Repeatable | 2 | Implement DLP solution to monitor sensitive data movement | IT Security | Q1 2027
13 | DE | DE.CM-06 | External service provider activities are monitored to find potentially adverse events | Tier 1 – Partial | Tier 3 – Repeatable | 2 | Add vendor access logging; review third-party activity monthly | IT Manager | Q4 2026
14 | DE | DE.AE-02 | Potentially adverse events are analyzed to characterize the events | Tier 1 – Partial | Tier 3 – Repeatable | 2 | Define incident triage process; create severity classification matrix | IT Security | Q3 2026
15 | DE | DE.AE-03 | Information is correlated from multiple sources | Tier 1 – Partial | Tier 3 – Repeatable | 2 | Configure log aggregation; correlate AV, firewall, and auth logs | IT Manager | Q4 2026
16 | RS | RS.MA-01 | The incident response plan is executed in coordination with relevant third parties | Tier 1 – Partial | Tier 3 – Repeatable | 2 | Draft and test incident response plan (use NIST SP 800-61) | IT Security | Q3 2026
17 | RS | RS.MA-02 | Incidents are triaged to support triage and escalation | Tier 1 – Partial | Tier 3 – Repeatable | 2 | Define incident severity tiers (P1–P4) with response SLAs | IT Security | Q3 2026
18 | RS | RS.MA-04 | Incidents are escalated or elevated as needed | Tier 1 – Partial | Tier 3 – Repeatable | 2 | Create escalation matrix and on-call rotation | IT Manager | Q3 2026
19 | RS | RS.AN-06 | Actions performed during an investigation are recorded | Tier 1 – Partial | Tier 3 – Repeatable | 2 | Implement evidence collection and chain of custody log template | IT Security | Q4 2026
20 | RC | RC.RP-01 | The recovery portion of the incident response plan is executed once initiated | Tier 1 – Partial | Tier 3 – Repeatable | 2 | Develop BCP and DRP; conduct tabletop exercise annually | IT Manager | Q4 2026
21 | RC | RC.RP-03 | The integrity of backups and other restoration assets is verified before using them | Tier 1 – Partial | Tier 3 – Repeatable | 2 | Schedule monthly backup restore tests; document results | IT Manager | Q3 2026
22 | RC | RC.RP-04 | Critical mission functions and cybersecurity considerations are established during recovery | Tier 1 – Partial | Tier 3 – Repeatable | 2 | Define RTOs and RPOs for all critical systems | IT Manager / Leadership | Q3 2026
23 | RC | RC.RP-05 | The integrity and security of assets is verified after all recovery activities | Tier 1 – Partial | Tier 3 – Repeatable | 2 | Create post-recovery verification checklist | IT Security | Q4 2026
24 | RC | RC.CO-03 | Recovery activities and progress in restoring operations are communicated to stakeholders | Tier 1 – Partial | Tier 3 – Repeatable | 2 | Draft stakeholder communication plan for recovery scenarios | Compliance Officer | Q4 2026
25 | GV | GV.OC-01 | Organizational mission is understood and informs cybersecurity risk management | Tier 3 – Repeatable | Tier 4 – Adaptive | 1 | Review and implement controls per NIST CSF guidance | IT Manager | Q4 2026
26 | GV | GV.OC-03 | Legal, regulatory, and contractual cybersecurity obligations are understood | Tier 2 – Risk Informed | Tier 3 – Repeatable | 1 | Review and implement controls per NIST CSF guidance | IT Manager | Q4 2026
27 | GV | GV.RR-01 | Cybersecurity roles and responsibilities are established and communicated | Tier 2 – Risk Informed | Tier 3 – Repeatable | 1 | Review and implement controls per NIST CSF guidance | IT Manager | Q4 2026
28 | GV | GV.PO-01 | Policy for managing cybersecurity risks is established, communicated, and enforced | Tier 2 – Risk Informed | Tier 3 – Repeatable | 1 | Review and implement controls per NIST CSF guidance | IT Manager | Q4 2026
29 | GV | GV.OV-01 | Cybersecurity review outcomes are communicated to stakeholders | Tier 2 – Risk Informed | Tier 3 – Repeatable | 1 | Review and implement controls per NIST CSF guidance | IT Manager | Q4 2026
30 | ID | ID.AM-01 | Inventories of hardware managed by the organization are maintained | Tier 2 – Risk Informed | Tier 3 – Repeatable | 1 | Review and implement controls per NIST CSF guidance | IT Manager | Q4 2026
31 | ID | ID.AM-02 | Inventories of software, services, and systems are maintained | Tier 2 – Risk Informed | Tier 3 – Repeatable | 1 | Review and implement controls per NIST CSF guidance | IT Manager | Q4 2026
32 | ID | ID.RA-01 | Vulnerabilities in assets are identified, validated, and recorded | Tier 2 – Risk Informed | Tier 3 – Repeatable | 1 | Review and implement controls per NIST CSF guidance | IT Manager | Q4 2026
33 | ID | ID.RA-03 | Internal and external threats to the organization are identified and recorded | Tier 2 – Risk Informed | Tier 3 – Repeatable | 1 | Review and implement controls per NIST CSF guidance | IT Manager | Q4 2026
34 | ID | ID.RA-05 | Threats, vulnerabilities, likelihoods, and impacts are prioritized | Tier 2 – Risk Informed | Tier 3 – Repeatable | 1 | Review and implement controls per NIST CSF guidance | IT Manager | Q4 2026
35 | ID | ID.IM-01 | Improvements are identified from security assessments | Tier 2 – Risk Informed | Tier 3 – Repeatable | 1 | Review and implement controls per NIST CSF guidance | IT Manager | Q4 2026
36 | PR | PR.AA-01 | Identities and credentials are issued, managed, verified, and revoked | Tier 2 – Risk Informed | Tier 3 – Repeatable | 1 | Review and implement controls per NIST CSF guidance | IT Manager | Q4 2026
37 | PR | PR.AA-02 | Identities are proofed and bound to credentials based on context | Tier 2 – Risk Informed | Tier 3 – Repeatable | 1 | Enforce MFA on VPN, email, and all remote access tools | IT Manager | Q3 2026
38 | PR | PR.AA-05 | Access permissions and authorizations are managed, incorporating least-privilege | Tier 2 – Risk Informed | Tier 3 – Repeatable | 1 | Review and implement controls per NIST CSF guidance | IT Manager | Q4 2026
39 | PR | PR.AT-01 | Personnel are provided with awareness and training so they can perform cybersecurity tasks | Tier 2 – Risk Informed | Tier 3 – Repeatable | 1 | Review and implement controls per NIST CSF guidance | IT Manager | Q4 2026
40 | PR | PR.DS-01 | Data-at-rest are protected | Tier 2 – Risk Informed | Tier 3 – Repeatable | 1 | Review and implement controls per NIST CSF guidance | IT Manager | Q4 2026
41 | PR | PR.DS-02 | Data-in-transit are protected | Tier 3 – Repeatable | Tier 4 – Adaptive | 1 | Review and implement controls per NIST CSF guidance | IT Manager | Q4 2026
42 | PR | PR.PS-01 | Configuration management practices are established and applied | Tier 2 – Risk Informed | Tier 3 – Repeatable | 1 | Apply CIS Benchmark Level 1 to all servers and workstations | IT Manager | Q4 2026
43 | PR | PR.PS-02 | Software is maintained, replaced, and removed commensurate with risk | Tier 2 – Risk Informed | Tier 3 – Repeatable | 1 | Review and implement controls per NIST CSF guidance | IT Manager | Q4 2026
44 | PR | PR.IR-01 | Networks and environments are protected from unauthorized logical access | Tier 2 – Risk Informed | Tier 3 – Repeatable | 1 | Review and implement controls per NIST CSF guidance | IT Manager | Q4 2026
45 | DE | DE.CM-09 | Computing hardware and software are monitored to find potentially adverse events | Tier 2 – Risk Informed | Tier 3 – Repeatable | 1 | Review and implement controls per NIST CSF guidance | IT Manager | Q4 2026
46 | DE | DE.AE-06 | Information on adverse events is provided to authorized staff and tools | Tier 2 – Risk Informed | Tier 3 – Repeatable | 1 | Review and implement controls per NIST CSF guidance | IT Manager | Q4 2026
47 | RS | RS.AN-03 | Analysis is performed to establish what has occurred during an incident | Tier 2 – Risk Informed | Tier 3 – Repeatable | 1 | Review and implement controls per NIST CSF guidance | IT Manager | Q4 2026
48 | RS | RS.CO-02 | Internal and external stakeholders are notified of incidents as required | Tier 2 – Risk Informed | Tier 3 – Repeatable | 1 | Review and implement controls per NIST CSF guidance | IT Manager | Q4 2026
49 | RS | RS.MI-01 | Incidents are contained | Tier 2 – Risk Informed | Tier 3 – Repeatable | 1 | Review and implement controls per NIST CSF guidance | IT Manager | Q4 2026
50 | RS | RS.MI-02 | Incidents are eradicated | Tier 2 – Risk Informed | Tier 3 – Repeatable | 1 | Review and implement controls per NIST CSF guidance | IT Manager | Q4 2026
51 | RC | RC.IM-01 | Recovery plans incorporate lessons learned | Tier 2 – Risk Informed | Tier 3 – Repeatable | 1 | Review and implement controls per NIST CSF guidance | IT Manager | Q4 2026

## Dashboard
NIST CSF 2.0 — EXECUTIVE DASHBOARD
Total Subcategories Assessed 51 |  |  | High-Priority Gaps 24 |  |  | Avg Current Tier 1.6 | Avg Target Tier 3.1
Function | Name | # Assessed | Avg Current Tier | Avg Target Tier | High-Pri Gaps | Overall Status
GV | GOVERN | 10 | 1.8 | 3.3 | 5 | Needs Attention
ID | IDENTIFY | 9 | 1.7 | 3 | 3 | Needs Attention
PR | PROTECT | 11 | 1.9 | 3.1 | 2 | In Progress
DE | DETECT | 7 | 1.3 | 3 | 5 | Critical
RS | RESPOND | 8 | 1.5 | 3 | 4 | Critical
RC | RECOVER | 6 | 1.2 | 3 | 5 | Critical
How to use this workbook: (1) CSF 2.0 Scorecard — full list of subcategories with current/target tiers. (2) Gap Analysis — per-function summary and tier legend. (3) Remediation Roadmap — prioritized action list. (4) Dashboard — this page. Update current tier scores in the Scorecard as controls mature.